## Template
<Project Name> Lessons Learned
Capture key takeaways at the end of your project. Keep it simple—use these lessons to improve future projects!
Category | What Worked Well | What Didn’t Work | Recommendation / Next Time | Owner

## Example
<Project Name> Lessons Learned
Capture key takeaways at the end of your project. Keep it simple—use these lessons to improve future projects!
Category | What Worked Well | What Didn’t Work | Recommendation / Next Time | Owner
Communication | Weekly team meetings kept everyone aligned | Leadership updates were inconsistent | Set a monthly leadership update cadence | Project Manager
Process | Clear task tracking in tracker | Requirements were unclear early on | Define requirements before execution | Project Team
Timeline | Milestones helped track progress | Deadlines slipped due to dependencies | Add buffer time to schedule | PM
Tools | Teams worked well for collaboration | Files stored in multiple locations | Centralize files in Teams/SharePoint | IT Lead