## Template
<Project Name> Project Log (Decisions, Risks, Issues)
Track key decisions, risks, and issues. Update throughout the project.
Type | Description | Impact | Owner | Date Logged | Status | Next Step | Notes

## Example
<Project Name> Project Log (Decisions, Risks, Issues)
Track key decisions, risks, and issues. Update throughout the project.
Type | Description | Impact | Owner | Date Logged | Status | Next Step | Notes
Decision | Use Teams for communication | High | Project Manager | 4/10/2026 | Closed |  | Agreed with team on 4/15/26
Risk | Delay in vendor delivery | High | Project Manager | 4/12/2026 | Open | Follow up with vendor
Issue | Missing requirements from department | Medium | Project Team | 4/14/2026 | Open | Schedule meeting